# HomeHelp

Development Roadmap

Customer Application — Sprint-by-Sprint Delivery Plan

26 weeks  •  13 two-week sprints  •  8 phases  •  3 releases (Alpha → Beta → GA)

# 1. How to Read This Roadmap

This roadmap sequences the 11 customer-app modules into 13 fixed sprints across 26 weeks. Weeks are relative to project kickoff (Week 1 = first working week); attach calendar dates at kickoff. Each sprint has a single goal, parallel Backend and Mobile tracks, integration/QA work, explicit dependencies and exit criteria (Definition of Done).

Cadence: 2-week sprints, demo + retro at each sprint end

Team: 1 squad: 2–3 Mobile (Flutter), 2–3 Backend, 1 DevOps, 1–2 QA, Tech Lead, PO/PM

Method: Scrum; design runs one sprint ahead of build

Critical path: Auth → Catalogue/Pricing → Booking → Slots → Payment → Tracking → Service execution

To compress to ~3.5–4.5 months, run Backend and Mobile as two parallel squads and overlap module sprints that have no hard dependency (e.g. Wallet alongside Payment, Profile alongside History).

# 2. Milestones & Releases

| Milestone | Achieved at | Outcome |
| --- | --- | --- |
| M0 — Foundations ready | End Sprint 0 (Wk 2) | Architecture, CI/CD, environments, design system, auth scaffolding |
| M1 — Authentication live | End Sprint 1 (Wk 4) | User can sign up / log in via OTP & Google |
| M2 — Booking configurable | End Sprint 4 (Wk 10) | Select services, type, date/time with availability |
| M3 — Bookable MVP (ALPHA) | End Sprint 6 (Wk 14) | Pay & confirm a booking; wallet working — internal alpha |
| M4 — Core journey complete | End Sprint 8 (Wk 18) | Track pro, OTP start, service progress to completion |
| M5 — Feature complete (BETA) | End Sprint 10 (Wk 22) | Reviews + booking history; closed beta release |
| M6 — Account & loyalty | End Sprint 11 (Wk 24) | Profile, addresses, payments, referrals, membership |
| M7 — GA Launch | End Sprint 12 (Wk 26) | Hardened, security-passed, store release |

## Release Gates

| Release | After | Audience | Go/No-Go Criteria |
| --- | --- | --- | --- |
| Internal Alpha | Sprint 6 | Internal team | End-to-end book→pay→confirm works on staging; no P1 defects |
| Closed Beta | Sprint 10 | Invited users | Full core journey + history; payment reconciliation verified; crash-free > 99% |
| Public GA | Sprint 12 | Public stores | Security review passed; SLA/perf targets met; UAT signed off |

# 3. Schedule Overview (Sprint Map)

| Sprint | Weeks | Phase | Focus | Module(s) |
| --- | --- | --- | --- | --- |
| 0 | 1–2 | Foundation | Architecture, CI/CD, design system | — |
| 1 | 3–4 | Phase 1 | Authentication | 1 |
| 2 | 5–6 | Phase 1 | Service catalogue & dynamic pricing | 2 |
| 3 | 7–8 | Phase 2 | Booking type selection | 3 |
| 4 | 9–10 | Phase 2 | Date/time & slot management | 4 |
| 5 | 11–12 | Phase 3 | Booking summary & payment | 5 |
| 6 | 13–14 | Phase 3 | Wallet (ALPHA release) | 10 |
| 7 | 15–16 | Phase 4 | Live tracking | 6 |
| 8 | 17–18 | Phase 4 | Arrival, OTP start, service progress | 7 |
| 9 | 19–20 | Phase 5 | Rate & review | 8 |
| 10 | 21–22 | Phase 5 | My bookings / history (BETA release) | 9 |
| 11 | 23–24 | Phase 6 | Profile, addresses, loyalty | 11 |
| 12 | 25–26 | Phase 7 | Hardening, security, perf, GA launch | All |

# 4. Sprint-by-Sprint Detail

## Sprint 0  (Weeks 1–2)

Goal: Establish the technical foundation so feature work can start cleanly.

### Backend

Repo structure, service skeletons, API gateway, base data schema (users, services, bookings)

Auth scaffolding (JWT + refresh), config & secrets management, logging framework

Provision Dev/Staging environments (PostgreSQL, Redis, object storage)

### Mobile

Flutter project setup, navigation shell, theming, reusable UI component library

App config, environment switching, API client + error handling layer

### Integrations / QA / DevOps

CI/CD pipelines (build, test, deploy), code scanning, crash reporting (Sentry)

Branching strategy, PR review process, ticket workflow

Dependencies: None (project kickoff)

Exit criteria (DoD): CI/CD green; skeleton app boots and calls a health endpoint across environments.

## Sprint 1  (Weeks 3–4)

Goal: A user can create an account and log in (Module 1).

### Backend

POST /auth/send-otp, /auth/verify-otp with OTP store (Redis), expiry & attempt limits

POST /auth/google token validation; account create/link; session issuance

Rate-limiting, masked-number logging, security hardening on auth

### Mobile

Login/Sign-up screen (+91, numeric validation, Continue gating), OTP screen

Continue-with-Google flow; Terms/Privacy webviews; error & retry states

### Integrations / QA / DevOps

Integrate SMS/OTP provider (MSG91/Twilio) and Google OAuth

Test cases TC-01…TC-12 for login; OTP edge cases

Dependencies: Sprint 0 foundation

Exit criteria (DoD): New & existing users can authenticate via OTP and Google on staging; auth test cases pass.

## Sprint 2  (Weeks 5–6)

Goal: A user can browse and select services with live pricing (Module 2).

### Backend

GET /services (categorised catalogue), POST /calculate-price (count + total, server-authoritative)

Service availability flags; pricing rules; analytics events

### Mobile

Service selection UI (multi-select, highlight, checkmark), category grouping

Real-time count & total, deselect, empty/₹0 state, Continue gating, unavailable badge

### Integrations / QA / DevOps

Pricing-failure handling test; rapid-selection & all-services edge cases (EC-01…EC-04)

Dependencies: Sprint 1 (authenticated session)

Exit criteria (DoD): Selecting/deselecting updates count & price in real time; pricing matches backend; tests pass.

## Sprint 3  (Weeks 7–8)

Goal: A user can choose how the service is delivered (Module 3).

### Backend

Booking draft model; booking-type persistence (instant/scheduled/recurring/custom)

Instant availability check (provider/area); recurring plan model; custom-request sanitisation

### Mobile

Single-select booking-type UI (radio behaviour), instant ETA display

Recurring frequency UI (daily/weekly/monthly/custom), custom-request form (500-char, photo, notes)

### Integrations / QA / DevOps

Service-area & availability validation; injection/HTML sanitisation tests (TC-01…TC-15)

Dependencies: Sprint 2 (selected services feed the draft)

Exit criteria (DoD): Exactly one booking type selectable and saved to draft; custom text sanitised; tests pass.

## Sprint 4  (Weeks 9–10)

Goal: A user can pick a valid date and time slot (Module 4).

### Backend

GET /availability/dates, /availability/slots; worker-availability logic (skills/distance/slot)

POST /booking/reserve-slot with Redis slot locking; service-duration computation; holiday/past rules

### Mobile

Calendar (block past/holidays), slot grid with statuses, single date+slot enforcement

Service-duration display, booking-summary preview, same-day slot filtering

### Integrations / QA / DevOps

Concurrency/overbooking tests; slot-becomes-unavailable edge case (EC-01)

Dependencies: Sprint 3 (booking draft + type)

Exit criteria (DoD): Valid date/slot reserved without overbooking; availability respects workers/holidays; tests pass. (Milestone M2)

## Sprint 5  (Weeks 11–12)

Goal: A user can review and pay for a booking (Module 5).

### Backend

Price breakdown (subtotal+fee+tax−discount), POST /payments/create-order, /payments/verify

Webhook handler + background reconciliation; idempotency; booking status → Confirmed; receipt/Booking ID

### Mobile

Booking summary (edit services, change address), price breakdown UI

Payment method selection (UPI/Card/NetBanking/Wallet/Pay Later), UPI deep-link, success/failure screens

### Integrations / QA / DevOps

Integrate payment gateway (Razorpay); duplicate-payment, timeout, network-fail tests (TC-01…TC-15, EC-01…EC-05)

Dependencies: Sprint 4 (reserved slot + total)

Exit criteria (DoD): Successful & failed payments handled; no double-charge; confirmed booking generated; reconciliation verified.

## Sprint 6  (Weeks 13–14)

Goal: Wallet works end-to-end and powers checkout (Module 10). → ALPHA

### Backend

Wallet + double-entry ledger, GET /wallet/balance, POST /wallet/add-money, /wallet/refund, transactions

Idempotent credits, negative-balance block, atomic concurrent ops, cashback (90-day expiry)

### Mobile

Wallet screen (balance, cashback, add money, ledger, filters), wallet-as-payment at checkout

Insufficient-balance prompt for additional method

### Integrations / QA / DevOps

Duplicate-callback & concurrency tests; wire refunds from cancellation flow

Cut Internal Alpha build; smoke-test full book→pay→confirm journey

Dependencies: Sprint 5 (payment + refund hooks)

Exit criteria (DoD): Top-up, wallet payment and refunds correct under concurrency; ALPHA released to internal team. (Milestone M3)

## Sprint 7  (Weeks 15–16)

Goal: A user can track the assigned professional live (Module 6).

### Backend

Assignment model; GET /booking/{id}/status, /booking/{id}/tracking; ETA via Maps Directions

WebSocket location pipeline; status engine (Assigned→On The Way→Arrived); POST /booking/cancel + refund

### Mobile

Live map (worker/customer markers, route, ETA badge), status timeline, professional card

Call (masked) + chat entry points, cancel with policy, GPS-loss/last-known handling

### Integrations / QA / DevOps

Google Maps integration; refresh intervals (10s/15s); reassignment & delay edge cases (EC-01…EC-05)

Dependencies: Sprint 5 (confirmed bookings) + worker-app/ops feed (mock if needed)

Exit criteria (DoD): Live location, ETA and status update within intervals; cancel triggers refund; tests pass.

## Sprint 8  (Weeks 17–18)

Goal: Service starts securely and progress is tracked to completion (Module 7).

### Backend

POST /booking/generate-otp, /verify-otp (4-digit, 10-min, 3 attempts, no reuse), bound to booking

Status: Arrived→Service Started→In Progress→Completed; service timer; GET /booking/progress/{id}

### Mobile

Arrival screen + OTP display, service-in-progress UI with timer/ETA

Contact professional, raise support, emergency escalation

### Integrations / QA / DevOps

Geofence (<100m) arrival; interruption/pause & customer-not-available edge cases; OTP tests (TC-01…TC-17)

Dependencies: Sprint 7 (assignment + tracking)

Exit criteria (DoD): Service starts only on valid OTP; progress/timer accurate to completion; tests pass. (Milestone M4)

## Sprint 9  (Weeks 19–20)

Goal: A user can rate and review a completed service (Module 8).

### Backend

POST /reviews, GET /reviews/{id}; worker average recompute; tag storage

Profanity/HTML filtering; low-rating (≤3) auto-ticket + ops notification; idempotent submit

### Mobile

Star rating (mandatory), review text (500-char counter), feedback tags, skip flow, Thank-You

Negative tags for low ratings; 5★ referral/loyalty prompt

### Integrations / QA / DevOps

Content-moderation & duplicate-submit tests; low-rating escalation (TC-01…TC-15, EC-01…EC-05)

Dependencies: Sprint 8 (completed service)

Exit criteria (DoD): Rating/review/tags stored, worker score updates, low ratings escalate; tests pass.

## Sprint 10  (Weeks 21–22)

Goal: A user can view, manage and rebook past bookings (Module 9). → BETA

### Backend

GET /bookings?status=, GET /booking/{id}, POST /support/create; pagination; search & filters

Rebook (pre-fill services), refund/cancellation display, deleted-worker handling, offline cache

### Mobile

Tabs (Upcoming/History/Cancelled), booking cards & details, view rating, Get Help, Rebook

Search, date filters, pagination, empty states

### Integrations / QA / DevOps

Large-history pagination & offline tests; cut Closed Beta build; beta onboarding

Dependencies: Sprints 5–9 (bookings, payments, reviews)

Exit criteria (DoD): History accurate across states; rebook & support work; BETA released to invited users. (Milestone M5)

## Sprint 11  (Weeks 23–24)

Goal: A user can manage their account, addresses, payments and loyalty (Module 11).

### Backend

GET/PUT /profile, /profile/addresses, /profile/payment-methods; referral & membership models

OTP-verified sensitive changes, device management, account-deletion workflow

### Mobile

Profile dashboard & edit, address CRUD (max 20, default), payment methods (max 10, default)

Security & privacy, notification preferences, Help & Support, Refer & Earn, stats, premium, logout

### Integrations / QA / DevOps

Invalid-email, duplicate-mobile, delete-default-address, referral-abuse edge cases (TC-01…TC-16)

Dependencies: Sprint 1 (auth) + Sprint 6 (wallet for referrals)

Exit criteria (DoD): Profile, addresses, payments, referrals & membership functional; sensitive changes OTP-verified. (Milestone M6)

## Sprint 12  (Weeks 25–26)

Goal: Harden, secure, optimise and ship to production. → GA

### Backend

Performance & load testing; payment/wallet reconciliation hardening; SLA alerting

Security review (OTP, PCI, injection, session, encryption); production infra & runbooks

### Mobile

End-to-end regression across all modules; crash/ANR fixes; store assets & release builds

Accessibility & device-matrix passes; analytics verification

### Integrations / QA / DevOps

UAT sign-off; staged rollout; Play Store & App Store submission and review

Disaster-recovery & backup verification; on-call setup

Dependencies: All prior sprints

Exit criteria (DoD): Security passed, SLA/perf targets met, UAT signed off; app live on both stores. (Milestone M7)

# 5. Critical Path & Dependencies

The booking-to-payment chain is the critical path; tracking and service execution depend on a confirmed booking and the professional/ops feed. De-risk by defining worker-app and admin interface contracts in Sprint 0 and using mock services until those apps are ready.

| Module | Depends on | Blocks |
| --- | --- | --- |
| 1 Auth | Foundation | Everything (authenticated session) |
| 2 Catalogue/Pricing | Auth | Booking draft & summary |
| 3 Booking Type | Catalogue | Scheduling |
| 4 Date/Time & Slots | Booking type | Summary & payment |
| 5 Payment | Slots + pricing | Confirmation, tracking, wallet refunds |
| 10 Wallet | Payment (refund hooks) | Checkout option, referral rewards |
| 6 Tracking | Confirmed booking + worker/ops feed | Service execution |
| 7 Service execution | Tracking + OTP service | Reviews |
| 8 Reviews | Completed service | Worker scoring, history rating |
| 9 History | Bookings/payments/reviews | Rebook & support |
| 11 Profile | Auth + wallet | Loyalty/referrals |

## External Dependencies to Secure Early

Payment gateway account & test keys (before Sprint 5)

Google Maps Platform keys & billing (before Sprint 7)

SMS/OTP provider & sender IDs (before Sprint 1)

Google OAuth client setup (before Sprint 1)

FCM / WhatsApp / Email providers (before Sprint 7)

Worker app + Admin/Ops panel interface contracts (Sprint 0) and working feeds (before Sprint 7)

# 6. Per-Sprint Definition of Done

All sprint user stories meet their documented acceptance criteria

Documented test cases (TC-xx) and edge cases (EC-xx) for the module pass in QA

Code reviewed, merged, and deployed to Staging via CI/CD

API contracts documented (OpenAPI) and analytics events emitted

No open P1/P2 defects; crash-free sessions above target

Demoed at sprint review and accepted by the Product Owner

# 7. Faster-Track Option (Two Parallel Squads)

With a Backend squad and a Mobile squad working in parallel and overlapping independent modules, the timeline compresses to roughly 14–18 weeks:

| Track | Weeks 1–4 | Weeks 5–9 | Weeks 10–14 | Weeks 15–18 |
| --- | --- | --- | --- | --- |
| Squad A | Foundation + Auth | Booking + Slots | Tracking + Service | Hardening |
| Squad B | Catalogue + Pricing | Payment + Wallet | Reviews + History | Profile + Launch |

Requires earlier external-dependency setup, strong interface contracts, and a shared QA/DevOps function to avoid integration bottlenecks.

— End of Roadmap —