## Worker App - Stories
HomeHelp Pro (Worker App) - Functionality, User Stories & Status
Legend: Completed = built & wired ¦ Partial = works but has a gap ¦ Pending = not done (assign to employee). Testing Status = QA state.
Module | Functionality | Description | User Story | Acceptance Criteria | Status | Note | Testing Status
Auth & Onboarding | OTP Login | Worker logs in with phone + OTP; token issued. | As a worker, I want to log in with my phone and OTP so I can access the app securely. | - Request OTP on valid phone - Verify OTP -> token issued - Wrong OTP rejected - Session persists on relaunch | Completed | Dev OTP 1234; live SMS (MSG91) not wired. | Ready to Test
| Profile setup / edit | View and edit name, city, services, avatar. | As a worker, I want to set up and edit my profile so admin and customers see accurate info. | - View profile from bootstrap - Edit + save persists - Reflects in Admin > Workers | Completed |  | Ready to Test
| Bank details | Add/update payout bank account + status. | As a worker, I want to add my bank details so I can receive payouts. | - Save bank + status - Shows verification status - Used by payout | Partial | Stored, but real payout not integrated (see Payouts). | Blocked
| KYC document upload | Upload ID / verification documents. | As a worker, I want to upload my KYC documents so I can be verified and take jobs. | - Pick file/image - Uploaded file stored + viewable by admin - Admin can verify/reject - Status shown to worker | Pending | GAP: backend stores only a filename string, not the file. No cloud storage; admin cannot view the image. | Blocked
Availability & Shifts | Online / offline toggle | Go online to be matched for jobs. | As a worker, I want to toggle online/offline so I control when I get jobs. | - Toggle sets available true/false - Only online workers matched - State persists | Completed |  | Ready to Test
| Shift booking (self-schedule) | Worker books shift slots for a day/zone. | As a worker, I want to book my shift slots so I commit to hours and get on-shift dispatch. | - See bookable shifts - Book a slot - On-shift drives auto-assign | Partial | Endpoint exists; demand-based slot opening (Snabbit-style) not built. Admin still rosters manually. | Not Tested
| Attendance check-in / out | Mark shift start/end (geofenced). | As a worker, I want to check in/out so my attendance and on-shift status are tracked. | - Check-in records time - Geofence report on start - Check-out closes shift | Completed |  | Not Tested
| Leave request | Request leave / days off. | As a worker, I want to request leave so I am not expected on those days. | - Submit leave - Shows in list - Admin visibility | Completed |  | Not Tested
Job Lifecycle | Real-time job alerts | Instant alert when a job is assigned/available. | As a worker, I want an instant alert for new jobs so I can accept quickly even if the app is closed. | - Push received when app killed/background - Sound + ongoing notification - Tapping opens the job | Pending | GAP: currently an 8s polling foreground service; NO FCM. No wake-from-killed; battery drain. | Blocked
| View available jobs | See matching open jobs. | As a worker, I want to see available jobs so I can pick one to do. | - List matches by service + zone - Distance/earnings shown | Completed |  | Not Tested
| Accept / Reject job | Claim or decline an offered job. | As a worker, I want to accept or reject an offered job so I control my workload. | - Accept claims (race-safe) - Reject skips it - Already-taken handled | Completed |  | Not Tested
| On the way / Arrived | Update travel status; share live location. | As a worker, I want to mark on-the-way/arrived so the customer sees my progress. | - Status updates propagate to customer - Live GPS shared | Completed |  | Not Tested
| Start (verify OTP) | Verify customer OTP to start the service. | As a worker, I want to verify the customer OTP so the service officially starts. | - Correct OTP -> in_progress - Wrong OTP rejected | Completed |  | Not Tested
| Complete / End job | Finish the job; optional work photo. | As a worker, I want to complete the job so it is marked done and I earn. | - End -> completed + timestamp - Earnings credited to ledger | Completed |  | Not Tested
| Cash collection / Settle | Collect cash and settle commission. | As a worker, I want to settle a cash job so the commission and earnings reconcile. | - Settle records cash collected - Commission deducted - Ledger updated | Partial | Wired; needs end-to-end verification with a real completed cash booking. | Blocked
| Cancel job | Cancel an assigned job with reason. | As a worker, I want to cancel a job (when necessary) with a reason so ops can track it. | - Cancel with reason - Returns to pool / penalty rules | Completed |  | Not Tested
Navigation & Map | Customer location on map | Show customer pin + route. | As a worker, I want to see the customer's location on a map so I can navigate. | - Map renders customer + my location - Route/navigation | Partial | GAP: Google Maps key is a placeholder (YOUR_API_KEY_HERE); falls back to OSM map. Add a real key or standardize on OSM. | Blocked
| Live location reporting | Report GPS while on a job. | As a worker, I want my location reported so the customer sees me move in real time. | - Periodic GPS post - Customer track updates | Completed |  | Not Tested
Earnings & Wallet | Earnings breakup | See per-job earnings and incentives. | As a worker, I want to see my earnings breakup so I understand what I earned. | - Income lines from ledger - Incentives shown | Completed |  | Not Tested
| Deductions | See commission/penalty deductions. | As a worker, I want to see deductions so my payout is transparent. | - Deduction lines - Net balance correct | Completed |  | Not Tested
| Wallet balance / history | Balance, on-hold, transaction history. | As a worker, I want to see my balance and history so I can track my money. | - Real balance from ledger - History list | Completed |  | Not Tested
| Withdraw / Payout | Request a withdrawal to bank. | As a worker, I want to withdraw my earnings so I actually receive the money. | - Request withdrawal - Money transferred to bank via RazorpayX - Status Processing -> Paid on real transfer - Failed payout auto-refunds to balance | Completed | DONE: RazorpayX payouts wired (contact -> fund account -> payout, bank/UPI) with webhook + ledger hold/withdraw/refund. Verified E2E in mock mode (success, idempotency, failure-refund). Add live keys (razorpay_key_id/secret, razorpayx_account_number, payout_mode, payout_webhook_secret) in Admin > Settings to move real money. NOTE: bank penny-drop verification still manual. | Passed
Notifications & Safety | Push notifications | System/status push notifications. | As a worker, I want push notifications so I do not miss jobs or updates. | - FCM device token registered - Server sends push on events | Pending | GAP: no FCM (same root as job alerts). Only in-app/polling now. | Blocked
| SOS / Emergency | Trigger SOS to admin control tower. | As a worker, I want an SOS button so I can get help in an emergency. | - SOS posts alert - Admin Live Ops receives it | Completed |  | Not Tested
Support | Support chat / tickets | Raise support tickets / chat. | As a worker, I want to contact support so I can resolve issues. | - Create ticket - View responses | Completed |  | Not Tested
Extras | Referral | Refer other workers. | As a worker, I want to refer others so I earn referral rewards. | - Referral code shown - Reward on qualifying referral | Completed |  | Not Tested
| Insurance / bonus | View insurance and bonus programs. | As a worker, I want to see insurance/bonus so I know my benefits. | - View insurance - File claim | Completed | Endpoints present; verify claim flow. | Not Tested
| Merchandise order | Order uniform/merch. | As a worker, I want to order merch so I have my kit. | - Browse - Place order | Completed |  | Not Tested
| Preferences / language | Set preferences and language (i18n). | As a worker, I want to set language/preferences so the app suits me. | - Change language - Save preferences | Completed | i18n present. | Not Tested

## Pending Gaps (Backlog)
Worker App - Pending Gaps (assign to employees)
# | Gap | Priority | Owner (suggested) | What to build | Acceptance
1 | Real-time job alerts (FCM) | High | Android dev | Firebase Cloud Messaging: register device token, server push on job.assigned/available, wake-from-killed, sound + ongoing notification. | Killed app receives job push in <5s; tapping opens the job.
2 | KYC document storage | High | Backend + Android | Store uploaded file bytes in cloud (S3/Cloudinary); admin view + verify/reject; worker sees status. | Uploaded image is viewable in Admin; verify/reject updates worker status.
3 | Real worker payouts | Done | Backend | DONE — RazorpayX payouts integrated (contact/fund-account/payout, bank + UPI), webhook, ledger hold/withdraw/refund, mock fallback. Just add live keys in Admin > Settings. | A withdrawal moves real money to the bank and marks Paid via webhook. [Verified E2E in mock mode]
4 | Google Maps key | Medium | Android dev | Add real Maps SDK key in AndroidManifest (or standardize on OSM fallback). | Map tiles render with worker + customer pins and route.
5 | Cash settlement E2E | Medium | QA + Backend | Verify collect-cash -> commission -> ledger for a real completed cash booking. | Completed cash job reconciles: earnings credited, commission deducted.
6 | Live OTP (SMS) | Medium | Backend | Wire MSG91/SMS so login OTP is real (currently dev OTP 1234). | Real SMS OTP delivered and verified.
7 | Customer payments (Razorpay) | High | Backend | Same Razorpay work; customer app is in demo/mock pay mode. | Real UPI/card charge succeeds and reconciles the booking.